## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | Your team name as "term-swen-261-02-5e-e5-20-news-1222"
Testing Team Name | @brendan Hoey (bdh5060), @aitan Bachrach (arb4414), @ayden Boyko (ajb7196), @liang Chu (lc2410), @dylan O'Hara (dbo8671)

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a customer I want to be able to create an account SO that I am able to login | Given I create an account when I login with the same username then I am accepted and login | PASS | LC; 10/23/22 LL 11/7/22 DP 11/7/22
AS a customer I WANT to be able to create an account SO that I can have my data persist between sessions | GIVEN a username that doesn't already exist in backend WHEN I click create account THEN an account with that username is created
AS a customer I WANT when I create an account to be automatically logged in SO I dont need to reenter my details | GIVEN my create account is successful WHEN I create an account THEN I am automatically logged in under that account
AS a customer I WANT to be able to access account only functions when I am logged in SO that I may utilize them | GIVEN I am logged in WHEN I go to access a account only function like a cart THEN I am able to do so
AS a customer I WANT to be unable to create an account with the same name as an already existing account | GIVEN a username that already exists within the system WHEN I click to create that account THEN the account creation fails and I informed that the username isn't valid
As a customer I want to be able to login to have access to a cart so that my data can persist | Given I log in with a username When I make changes to the cart then I want the data to be saved | PASS | LC: 10/23/22 LL 11/7/22 DP 11/7/22
As a customer I want to be able to add candies to my cart so that I can purchase them | Given I am logged in When I add a candy to my cart I can see it reflected in my cart | PASS | LC: 10/23/22 LL 11/7/22 DP 11/7/22
AS a customer I WANT to be able to have candies in my cart persis SO that I may purchase them at a later time | GIVEN I had a candy in my cart and I logged out WHEN I log back in THEN the candy is still in my cart
AS a customer I WANT to be able to puchase my cart SO that my order can be submitted | GIVEN some amount of candies in my cart WHEN I purchase my cart THEN my cart is cleared and the appropriate order is made
AS an owner I WANT when a customer purchases a cart that the corresponding candies are removed from the inventory SO that the inventory is always reflective of what we have | GIVEN a customer has a some candies in their cart WHEN they purchase it THEN the appropriate amount is subtracted from the inventory
AS a customer I WANT to be able to remove candies form my cart SO that I have better manipulation of what is in my cart | GIVEN a candy in my cart WHEN i remove that candy THEN the candy is no longer in my cart
AS a customer I WANT the removal of a candy to persist between sessions SO that candies in my cart stay removed | GIVEN I removed a candy from my cart and logged out WHEN I log back in THEN the candy is still reflected as being out of my cart
AS a customer I WANT to be able to increase the amount of a candy in my SO that I may decide how much of a candy I am purchasing | GIVEN I have a candy in my cart WHEN I increase the amount of that candy THEN the amount of candy in my cart increases
AS a customer I WANT to be able to decrease the amount of candy in my cart SO that I candecide how much of a candy I am purchasing | GIVEN I have a candy in my cart WHEN I decrease the amount of that candy THEN the amount of candy in my cart decreases
AS a customer I WANT the increase of a quantity of a candy to persist between sessions SO that I can manipulate my cart and be able to return to it later | GIVEN I increase the quantity of a candy in my cart and log out WHEN I log back in THEN the amount of candy in my cart has persisted
As a customer I WANT the decrease of a quantity of a candy to persist between sessions SO that I can manipulate my cart and be able to return to it later | GIVEN I decrease the quantity of a candy in my cart and log out WHEN I log back in THEN the amount of candy in my cart has persisted
As a customer I WANT when I decrease the quanity of a candy in my cart to 0 to then remove that candy from my cart SO that I am not confused about whether or not a candy in in my cart | GIVEN a candy in my cart WHEN I decrease the quantity of a candy in my cart to 0 THEN the candy is removed from my cart |  | LL 11/7/22 glitches out, quantity goes to negative for certain occasions
AS a customer I WANT to be unable to increase the amount of a candy in my cart beyond what the store has in stock SO that I can't make my cart invalid | GIVEN a candy in my cart WHEN I go to increase the amount of it in my cart beyond what is it stock THEN I am unable to do so
AS a customer I WANT to be unable to purchase a cart that has been made invalid SO that I can be sure I can recieve my order | GIVEN a candy in my cart that has been made invalid WHEN I go to purchase that cart THEN I am unable to do so
AS a customer I WANT to be informed about when I have an invalid candy as well as which candy is invalid SO that I can know which candy I need to remove/correct | GIVEN a candy in cart has been made invalid WHEN I look at my cart THEN I can tell which candy I have an invalid amount of in my cart
As a user I want to be able to browse the available inventory so that I can see what Is available | Given some candies in stock When I view them all Then I can see all candies in stock | PASS | AB 10/23 LL 11/7/22 DP 11/7/22
AS an owner I WANT to be able to login as an admin SO that I can then access the ability to change data about the shop | GIVEN I enter the username 'admin' WHEN I click login THEN I am logged in as an admin and can access the admin components
AS an owner I WANT to not have access to customer specific functions SO that I am focused only on modifing the shop as an admin | GIVEN I am logged in as admin WHEN I try to access the functions specific to a customer THEN I am unable to do so
As the Estore Owner I want to add items to inventory as an admin so that I can see those products(the candies) being listed on. | Given I am logged in when I add a candy to the inventory data then I expect to be able to view them to the e-store website | PASS | AB 10/23 LL 11/7/22 DP 11/7/22
As the Estore Owner I want to add items to inventory with just the name of the product at the bare minimum as an admin so that I can see those products(the candies) being listed on. | Given I am logged in when I add a candy to the inventory data with just the name of Candy then I expect to be able to view them to the e-store website with the Candy name and the default values for the other parameters.
As the Estore Owner I should not be able to add items to the inventory if I don't have the name of the product at least. | Given I am an admin when I log in under the estore website, then I should not be able to add candy to the inventory if I don't have the name of said candy at the very least
As an Owner I want to remove items from inventory as an admin so that I can not see those products(the candies) being listed. | Given I am logged in when I remove candy from the inventory data then I expect to not be able to view them to the e-store website | PASS | AB 10/23 LL 11/7/22 DP 11/7/22
As an Owner I want to edit the data inventory as an admin so that I can see the change of products(the candies) being listed. | Given I am logged in when I edit the items in the inventory data then I expect to see a change of products listed in the e-store website | PASS | AB 10/23 LL 11/7/22 DP 11/7/22
AS an owner I WANT to be unable to enter invalid date for the fields of amount and price when creating a candy SO that I can't accidentaly enter data that doesn't make any sense | GIVEN I am logged in as adming WHEN I enter data that is invalid for creating a candy THEN I expect the values that either weren't entered or were invalid to become 0
AS a owner I WANT to be unable to update a candies values to be invalid SO that I can't accidentaly enter values that make no sense | GIVEN I am logged in as an admin WHEN I update a candy with values that don't make sense THEN I expect the values to not actually get updated
As a Customer I want to see the ratings of every candy so that I can see what other people think about purchasing that particular candy at the e-store. | Given I am logged in, when I click "see reviews" on a particular item, then I expect to be able to see the reviews on said item. |  |  | IN DEVELOPMENT
As a Buyer I want to be able to leave ratings for every candy so that I can express my thoughts on the candy to other people who think about purchasing that particular candy at the e-store. | Given that I am viewing the item when I click "review" on said item, then I expect to be able to leave a review on the item. |  |  | IN DEVELOPMENT
AS a customer I WANT my rating to be saved SO that other customers can see it | GIVEN I have rated a candy and logged out WHEN I log back THEN I can see my rating has persisted
AS a customer I WANT to be able to add a small mystery box to my cart SO that I can then purchase it | GIVEN I have added a small mystery box to my cart WHEN I view my cart THEN I can see it there
AS a customer I WANT to be able to add a large mystery box to my cart SO that I can then purchase it | GIVEN I have added a large mystery box to my cart WHEN I view my cart THEN I can see it there
AS a customer I WANT to be able to increase the quantity of a mystery box in my cart SO that I can control how many I am purchasing | GIVEN I have a mystery box in my cart WHEN I increase the quantity in my cart THEN the quantity in my cart increases
AS a customer I WANT to be able to decrease the quantity of mystery box in my cart SO that I can control how many I am purchasing | GIVEN I have a mystery box in my cart WHEN I decrease the amount of the mystery box in my cart THEN the quantity in my cart decreases
AS a customer I WANT to be able to remove a mystery box from my account SO that i don't need to purchase it even if it is added to my cart | GIVEN I have a mystery box in my cart WHEN I remove the mystery box from my cart THEN it is removed from my cart
AS a customer I WANT the changes i make to mystery boxes in my cart to persist between sessions SO that I mkae changes and the purchase at a later date | GIVEN I have or had a mystery box in my with some amount WHEN I log out and log back in THEN the changes I made to the mystery box have persisted
AS a owner I WANT when a customer purchases a mystery box for the candies they receive in that mystery box to be removed from the inventory properly SO that the inventory stays up to date | GIVEN a customer has a a mystery box in their cart WHEN they purchase it THEN the candies contained within that mystery box are subtracted from the current inventory
AS a customer I WANT to recieve a random assortment of candies when I purchase a mystery box SO that I may then try them | GIVEN a mystery box in my cart WHEN I purchase it THEN I a number of randomly chosen candies based on the size of the box
AS a customer I WANT to see the total price of the candies I am purchasing SO that I can know how much my order will cost | GIVEN I have some amount of candies in my cart WHEN I am looking at my cart THEN the total price of the candies is displayed
AS a customer I WANT to see a reciept after I have completed a purchase SO that I can know what I have bought including what was inside my mystery box | GIVEN I have some amount of candies and or mystery boxes in my cart WHEN I complete my purchases THEN I see a reciept that shows every candy I have purchased including what was inside the mystery boxes
AS a customer I WANT the site to be visually appealing and easy to understand SO that I have an easy time navigating the site and understanding what information is being displayed to me | GIVEN I am browsing the site WHEN I look at the site THEN is appealing visually and the information being presented is easy to understand
AS a developer I WANT the code to better adhere to OO design principles SO that I have an easier time understanding what the code is trying to accomplish | GIVEN I am looking at the code WHEN I try to figure out what it is doing THEN it is easy to do so
AS a customer I WANT to only be able to submit one rating per candy SO that the rating I see isn't being dragged up or down based on only one customer's opinion | GIVEN I have rated a candy WHEN I try to do so again THEN my rating isn't counted
AS a customer I WANT to be unable to purchase a my cart if there isnt enought candies to finalize my purchase of a mystery box SO that I can't buy something that wont be fufilled | GIVEN I have a mystery box in my cart and there are not enough candies in inventory to complete the order WHEN I go to try ot purchase my cart THEN I am unable to do so